## Risk Register
Write risks as cause, event, and consequence. Rating and residual columns calculate automatically from likelihood and impact.
Risk ID | Risk description | Category | Likelihood | Impact | Rating | Level | Owner | Treatment | Controls / actions | Target rating | Residual rating | Accepted by | Date accepted | Next review
R-001 | Because AI systems are procured without governance review, unassessed high-risk systems may go live, leading to regulatory breach and enforcement | Compliance | 4 | 4 |  |  | [name] | Treat | Mandatory intake gate; quarterly SaaS sweep | 8
R-002 | Because training data under-represents some groups, the model may produce discriminatory outcomes, leading to harm and legal claims | Fairness | 3 | 5 |  |  | [name] | Treat | Representativeness testing at G4; subgroup metrics | 6
Note on A3: Stable reference, e.g. R-001.
Note on B3: Because [cause], [event] may happen, leading to [consequence].
Note on C3: Risk type.
Note on D3: 1 Rare … 5 Almost certain.
Note on E3: 1 Negligible … 5 Severe.
Note on F3: Likelihood x Impact. Calculated.
Note on G3: Calculated from the rating.
Note on H3: Named person accountable for treating it.
Note on I3: Tolerate requires a named acceptor.
Note on J3: What is actually being done.
Note on K3: Where you expect to get to.
Note on L3: Where you actually are after treatment.
Note on M3: Required if tolerating. Risk tolerated by nobody has been ignored.
Note on N3: Date.
Note on O3: Critical monthly, High quarterly, Medium half-yearly, Low annually.

## About
Risk Register
The live record of data and AI risks: what could go wrong, how likely and how bad, what you are doing about it, and who owns it.
How to use it: Write risks as cause, event, and consequence — "because X, Y may happen, leading to Z". A register full of one-word risks like "data quality" cannot be managed, because nobody can tell what treating it would involve.
Columns carry a comment explaining what belongs in them — hover the header.
Grey dropdown columns are constrained to the listed values.
From the Open Data & AI Governance Kit — https://lsdeva.github.io/governance-kit/
Licensed CC BY 4.0. Free to use, adapt, and share with attribution.
Not legal advice. Adapt to your jurisdiction, sector, and risk appetite, and have qualified counsel review anything material.